⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES Cobbleway Home Services Ltd is not a real business. Names, dates, budgets and results are invented to practise project-management methods from my MSc studies. Nothing here describes a real client or real outcomes.

Project charter and business case

Project Compass: CRM implementation · Cobbleway Home Services Ltd (fictional)

| Document | Project charter and outline business case, v1.0 (approved) |
| --- | --- |
| Project | Project Compass: CRM implementation |
| Organisation | Cobbleway Home Services Ltd: a fictional 25-person plumbing, heating and electrical firm in North East England (14 field engineers, 2 apprentices and a 9-person office and management team) |
| Sponsor / Executive | Helen Marsh, Managing Director (fictional) |
| Project manager | Chidera Ikenna-Obi (simulated role, MSc practice project) |
| Approval | Approved at M1 on 11 Mar 2026 |
| Related artefacts | 02 Requirements and stakeholder register · 03 WBS and schedule · 04 RAID log · 05 RACI and communications plan · 06 Status dashboard |

# 1. Background and problem

Cobbleway Home Services Ltd handles around 1,100 quotes a year (illustrative) for boiler installs, servicing, repairs and small electrical jobs. Enquiries arrive by phone, email and a website form and are tracked across a shared inbox, two spreadsheets and a whiteboard. There is no single customer record, follow-ups depend on memory, and job details are re-keyed into the accounting package.

Lost work: quotes are not followed up consistently, so winnable jobs go elsewhere.

Slow response: a quote takes about five working days to go out.

Missed repeat revenue: annual boiler-service reminders are sent by hand, when someone remembers.

Wasted time: the office re-keys roughly eight hours of data a week.

# 2. Objectives

| # | Objective (SMART) | Measure |
| --- | --- | --- |
| O1 | Go live with a cloud CRM for all office staff and 6 lead engineers by 20 May 2026 | Go-live milestone M6 |
| O2 | Deliver within the approved budget of £36,500 (including £3,500 contingency) | Final cost vs budget |
| O3 | Deliver all Must requirements (REQ-01 to REQ-08) | UAT sign-off |
| O4 | Log 100% of new enquiries in the CRM within 2 weeks of go-live | CRM report vs call log |
| O5 | Cut quote turnaround to 2 working days within 6 months | Benefits review |

# 3. Scope

## In scope

Selection and configuration of a SaaS CRM (enquiries, quotes, pipeline, jobs, service reminders)

Integration with email and the existing accounting package

Mobile access for engineers on 6 rugged tablets

Cleansing and migration of active customer records (last 6 years)

Training, quick-reference guides, a champions network and two weeks of hypercare

## Out of scope

Replacing the accounting package (REQ-17)

Route optimisation for scheduling (REQ-18)

Website redesign

Migrating records older than 6 years (archived under the retention rule)

# 4. Business case

## Options appraisal

| Option | One-off cost | Benefit | Risk | Decision |
| --- | --- | --- | --- | --- |
| 1. Do nothing | £0 | None; losses continue | Low delivery risk, high business risk | Rejected |
| 2. Improve spreadsheets and shared inbox | ~£4,000 | Low: still no single record or reminders | Low | Rejected |
| 3. SaaS CRM, configured by a partner | £36,500 incl. contingency | High: meets all Must and most Should needs | Medium (data, adoption) | Recommended |
| 4. Bespoke system | £60,000+ | High, but slow to deliver | High (cost, time, support) | Rejected |

## Costs (option 3)

| Category | Budget |
| --- | --- |
| CRM licences (18 users, year 1) | £6,800 |
| Supplier configuration and integration | £9,500 |
| Data migration and cleansing | £4,200 |
| Training and materials | £3,000 |
| Internal staff time (backfill) | £6,000 |
| Hardware (6 rugged tablets and cases) | £3,500 |
| Base budget | £33,000 |
| Contingency (about 10%) | £3,500 |
| Total approved budget | £36,500 |

## Expected benefits (illustrative estimates)

| Benefit | Baseline | Target | How measured | Owner |
| --- | --- | --- | --- | --- |
| Quote turnaround | ~5 working days (estimate) | 2 working days | CRM report: enquiry to quote sent | Tom Reilly |
| Quotes followed up | ~40% (estimate) | 90% | Pipeline follow-up tasks completed | Tom Reilly |
| Admin re-keying | ~8 hours a week | Save 6 hours a week (~£5,000 a year) | Time sample before and after | Priya Shah |
| Boiler-service bookings from reminders | No automated reminders | +120 bookings a year (~£10,200) | Service jobs created from reminders | Dave Pearson |
| Quote conversion | ~32% (estimate) | +3 percentage points (~£8,000 margin a year) | Won / sent quotes | Helen Marsh |

## Three-year view

|  | Year 1 | Year 2 | Year 3 | Total |
| --- | --- | --- | --- | --- |
| Costs (project, then licences and support) | £36,500 | £7,100 | £7,300 | £50,900 |
| Benefits (half-year realisation in year 1) | £11,600 | £23,200 | £23,200 | £58,000 |
| Net | −£24,900 | +£16,100 | +£15,900 | +£7,100 |

Payback is expected during year 3 (around month 30). The case depends most on adoption by engineers and office staff (risk R02), so benefits will be reviewed at 3 and 6 months after go-live.

# 5. Milestones (baseline)

| Milestone | Baseline date | Approver |
| --- | --- | --- |
| M1 Charter and business case approved | 11 Mar 2026 | Helen Marsh |
| M2 Requirements signed off | 24 Mar 2026 | Dave Pearson |
| M3 Supplier selected and contract signed | 07 Apr 2026 | Helen Marsh |
| M4 Configuration complete | 12 May 2026 | Sam Carter |
| M5 Go/no-go decision | 18 May 2026 | Helen Marsh |
| M6 Go-live | 20 May 2026 | Helen Marsh |
| M7 Project closed | 10 Jun 2026 | Helen Marsh |

# 6. Governance and tolerances

Governance follows PRINCE2 principles covered in my MSc module (Managing Projects with PRINCE2): a small project board, management by stages and management by exception against agreed tolerances.

| Role | Name | Responsibility |
| --- | --- | --- |
| Executive (Sponsor) | Helen Marsh | Owns the business case; approves stages, changes over £500 and go/no-go |
| Senior User | Dave Pearson | Represents users; signs off requirements and UAT |
| Senior Supplier | Sam Carter (Northlight CRM Partners, fictional) | Delivers configuration, integration and migration |
| Project Manager | Chidera Ikenna-Obi (simulated role) | Day-to-day planning, RAID, reporting and change control |
| Lead CRM Champion | Priya Shah | Data rules, training, champions network |

| Tolerance | Level | If forecast to be exceeded |
| --- | --- | --- |
| Time | ±1 week (5 working days) on go-live | Exception report to sponsor |
| Cost | Up to £3,500 contingency, released by the sponsor | Exception report; re-plan |
| Scope | Must requirements fixed; Should/Could can be traded | Change request |

# 7. Key risks (see RAID log)

| ID | Risk | P × I | Response |
| --- | --- | --- | --- |
| R01 | Poor legacy data quality delays migration | 4×4 = 16 | Reduce: data audit in week 3; cleansing rules agreed; supplier-assisted de-duplication |
| R02 | Field engineers do not adopt the mobile app | 3×4 = 12 | Reduce: Field Supervisor co-designs screens; champions; short hands-on training; usage tracked in hypercare |
| R03 | Accounting integration more complex than quoted | 3×4 = 12 | Reduce: supplier technical call before contract; contingency held |
| R06 | Customer data migrated without proper retention review | 2×5 = 10 | Reduce: 6-year retention rule; records older than this archived, not migrated; privacy notice updated |
| R04 | Key staff unavailable for UAT and training | 3×3 = 9 | Reduce: dates booked at M2; backfill budget; two training sessions per group |

# 8. Assumptions, constraints and dependencies

18 named CRM users is enough for year 1 (office team plus 6 tablet users)

Key users can give one day a week to workshops, UAT and training

The existing accounting package stays in place

Office broadband and engineers' 4G are adequate for a cloud CRM

Constraint: go-live must avoid the October to December heating peak.

Dependency: accounting package API access (D01) and tablet delivery (D02).

# 9. Approval

| Role | Name | Decision | Date |
| --- | --- | --- | --- |
| Sponsor | Helen Marsh | Approved | 11 Mar 2026 |
| Senior User | Dave Pearson | Endorsed | 11 Mar 2026 |