## Requirements (MoSCoW)
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
Requirements catalogue (MoSCoW)
Project Compass: CRM implementation · v1.0 signed off 24 Mar 2026 by Dave Pearson (Senior User) · status column updated at closure
ID | Priority | Requirement | Acceptance criterion | Owner | Status at closure
REQ-01 | Must | Single customer record holding contacts, properties, appliances and job history | Any customer's full history found in under 30 seconds in UAT | Priya Shah | Delivered
REQ-02 | Must | Log enquiries from phone, email and the website form in one queue | All three channels create an enquiry with source recorded | Priya Shah | Delivered
REQ-03 | Must | Create and send quotes from templates, with VAT calculated correctly | Quote PDF produced and emailed from the record; VAT correct to the penny | Tom Reilly | Delivered
REQ-04 | Must | Sales pipeline with stages and automatic follow-up tasks | Follow-up task created 3 working days after a quote is sent | Tom Reilly | Delivered
REQ-05 | Must | Job records linked to customer and quote, assignable to an engineer | Accepted quote converts to a job in one step | Dave Pearson | Delivered
REQ-06 | Must | Mobile access for engineers: job details, notes, photos and customer sign-off | Engineer completes a job end to end on a tablet in UAT | Gary Hodgson | Delivered
REQ-07 | Must | Migrate active customers (last 6 years) with duplicates removed | Reconciliation report: record counts match; duplicate rate under 1% | Priya Shah | Delivered
REQ-08 | Must | Role-based access and UK GDPR-aligned retention rules | Engineers see only assigned jobs; retention rule applied to inactive records | Helen Marsh | Delivered
REQ-09 | Should | Automated annual boiler-service reminders by email and SMS | Reminder sent 30 days before the service due date | Priya Shah | Delivered
REQ-10 | Should | Sync invoices and customers with the existing accounting package | Invoice raised in CRM appears in accounting within 15 minutes | Lucy Bell | Partly delivered (one-way sync; two-way in backlog)
REQ-11 | Should | Log emails against the customer record | Shared-inbox emails attach to the matching customer | Ben Ward | Delivered
REQ-12 | Should | Management reports: pipeline value, conversion rate, quote turnaround | Weekly report available to the MD without manual work | Dave Pearson | Delivered
REQ-13 | Should | Offline mode for the mobile app in low-signal areas | Job notes captured offline sync when signal returns | Gary Hodgson | Delivered
REQ-14 | Could | Customer online booking portal | Customers can request a service slot online | Tom Reilly | Deferred to backlog
REQ-15 | Could | Post-job customer satisfaction survey | Survey sent automatically when a job is closed | Priya Shah | Delivered
REQ-16 | Could | Van stock tracking | Stock used on a job deducted from van stock | Gary Hodgson | Deferred to backlog
REQ-17 | Won't | Replace the accounting package (out of scope this phase) | n/a | Lucy Bell | Not in scope (as agreed)
REQ-18 | Won't | Route optimisation for engineer scheduling (out of scope this phase) | n/a | Dave Pearson | Not in scope (as agreed)
|  | Summary (formulas) | Count | Delivered
|  | Must | 0 | 0
|  | Should | 0 | 0
|  | Could | 0 | 0
|  | Won't | 0 | 0

## Stakeholder register
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
Stakeholder register (power / interest)
Power and interest scored 1 (low) to 5 (high). Quadrant is calculated: power ≥3 and interest ≥3 = Manage closely.
Stakeholder | Role | Organisation | Power | Interest | Quadrant | Key interest / concern | Current | Desired | Engagement approach | Relationship owner
Helen Marsh | Managing Director, Project Sponsor | Cobbleway | 5 | 5 | 0 | Return on investment; less lost work; no disruption to customers | Supportive | Leading | Fortnightly sponsor 1:1; owns go/no-go and tolerances | Chidera Ikenna-Obi
Dave Pearson | Operations Manager, Senior User | Cobbleway | 4 | 5 | 0 | Job scheduling works on day one; engineers' time protected | Supportive | Leading | Weekly project meeting; signs off requirements and UAT | Chidera Ikenna-Obi
Priya Shah | Office Manager, Lead CRM Champion | Cobbleway | 3 | 5 | 0 | Workload during data cleansing; ease of use for the office team | Neutral | Leading | Champion role; involved in design and data rules; backfill agreed | Chidera Ikenna-Obi
Tom Reilly | Sales and Estimating Lead | Cobbleway | 3 | 5 | 0 | Quote templates and follow-ups; pipeline visibility | Supportive | Supportive | Requirements workshops; quote template owner | Chidera Ikenna-Obi
Gary Hodgson | Field Supervisor | Cobbleway | 3 | 4 | 0 | Extra admin for engineers; reliability of the mobile app | Resistant | Supportive | Early demo; co-designs mobile job screens; leads engineer training | Dave Pearson
Field engineers (14) and apprentices (2) | End users (mobile) | Cobbleway | 2 | 4 | 0 | Simple screens; no extra paperwork; works with poor signal | Neutral | Supportive | Toolbox talks; short hands-on sessions; quick-reference cards | Gary Hodgson
Customer service coordinators (3) | End users (office) | Cobbleway | 2 | 5 | 0 | Learning a new system in peak season | Neutral | Supportive | Champions network; training before go-live; floor-walking in hypercare | Priya Shah
Lucy Bell | Finance and Admin Officer | Cobbleway | 2 | 3 | 0 | Invoices reconcile with the accounting package | Neutral | Supportive | Integration testing owner; monthly budget review | Chidera Ikenna-Obi
Sam Carter | Implementation Consultant, Senior Supplier | Northlight CRM Partners (fictional) | 4 | 2 | 0 | Clear requirements; change requests handled formally | Supportive | Supportive | Weekly supplier check-in; change control | Chidera Ikenna-Obi
Ben Ward | IT Support Contractor | Quayside IT (fictional) | 2 | 2 | 0 | Email domain and device set-up requests on time | Neutral | Supportive | Ticketed requests with two weeks' notice | Chidera Ikenna-Obi
Customers | Homeowners and small businesses | External | 1 | 2 | 0 | Service unaffected; reminders and quotes arrive on time | Unaware | Neutral | No direct engagement; monitor complaints through go-live | Priya Shah

## Power-interest grid
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
Power / interest grid
Counts are formulas on the register; names listed for quick reading.
HIGH POWER | 0 | 0
| • Sam Carter | • Helen Marsh • Dave Pearson • Priya Shah • Tom Reilly • Gary Hodgson
LOW POWER | 0 | 0
| • Ben Ward • Customers | • Field engineers (14) and apprentices (2) • Customer service coordinators (3) • Lucy Bell
| LOW INTEREST → | HIGH INTEREST →