## Risks
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
RAID log: risks
Score = probability × impact (1–5 each). 15+ = Red, 8–14 = Amber, 1–7 = Green. Final version at closure (16 Jun 2026).
ID | Risk | Cause and effect | Raised | Owner | Prob. | Impact | Score | Rating | Response (strategy: action) | Status | Closed | Notes
R01 | Poor legacy data quality delays migration | Customer spreadsheet and old job software contain duplicates and missing addresses, so cleansing could overrun | 2026-03-09 | Priya Shah | 4 | 4 | 0 | 0 | Reduce: data audit in week 3; cleansing rules agreed; supplier-assisted de-duplication | Closed | 2026-05-18 | Occurred as issue I01; go-live moved 4 working days (within the 5-day time tolerance)
R02 | Field engineers do not adopt the mobile app | Engineers see the app as extra admin, so job updates stay on paper and benefits are lost | 2026-03-09 | Gary Hodgson | 3 | 4 | 0 | 0 | Reduce: Field Supervisor co-designs screens; champions; short hands-on training; usage tracked in hypercare | Open |  | Transferred to BAU owner (Dave Pearson) at closure
R03 | Accounting integration more complex than quoted | The accounting package may need a paid connector, adding cost and time | 2026-03-23 | Lucy Bell | 3 | 4 | 0 | 0 | Reduce: supplier technical call before contract; contingency held | Closed | 2026-04-27 | Occurred as issue I02; resolved by change request CR01
R04 | Key staff unavailable for UAT and training | Peak boiler-servicing season and Easter leave reduce availability | 2026-03-16 | Dave Pearson | 3 | 3 | 0 | 0 | Reduce: dates booked at M2; backfill budget; two training sessions per group | Closed | 2026-05-15 | Sessions delivered as planned
R05 | Supplier resourcing slips configuration | Implementation partner has competing projects | 2026-04-02 | Sam Carter | 2 | 4 | 0 | 0 | Reduce: named consultant in contract; weekly check-in | Closed | 2026-05-12 | Configuration completed (M4)
R06 | Customer data migrated without proper retention review | Inactive records kept with no lawful basis could breach UK GDPR | 2026-03-16 | Helen Marsh | 2 | 5 | 0 | 0 | Reduce: 6-year retention rule; records older than this archived, not migrated; privacy notice updated | Closed | 2026-05-27 | Retention rule applied in final migration
R07 | Change requests push cost over tolerance | Further integration or reporting requests could exceed the 10% contingency | 2026-04-13 | Chidera Ikenna-Obi | 3 | 3 | 0 | 0 | Reduce: change control; sponsor approves any CR over £500 | Closed | 2026-06-16 | Final cost within budget including contingency
R08 | Low mobile signal stops job updates | Rural jobs in parts of County Durham have weak 4G coverage | 2026-03-23 | Ben Ward | 3 | 2 | 0 | 0 | Reduce: offline mode (REQ-13) tested in UAT at two low-signal sites | Closed | 2026-05-15 | Offline sync passed UAT
R09 | Go-live disrupts customer service | Cut-over during a busy week could mean missed calls or lost enquiries | 2026-04-20 | Priya Shah | 2 | 4 | 0 | 0 | Reduce: cut-over outside the Monday peak; shared inbox monitored in parallel for two weeks; hypercare rota | Closed | 2026-06-10 | No lost enquiries logged during hypercare

## Issues
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
RAID log: issues
ID | Issue | Raised | Owner | Severity | Action / resolution | Status | Closed
I01 | Around 18% of legacy customer records are duplicates | 2026-04-21 | Priya Shah | High | Two extra cleansing weeks agreed; supplier de-duplication script; trial migration and UAT moved back 4 working days | Closed | 2026-05-13
I02 | Accounting package needs a paid connector for invoice sync | 2026-04-16 | Lucy Bell | Medium | CR01 raised and approved (£900, +3 days); two-way sync deferred to backlog | Closed | 2026-04-27
I03 | Two tablets faulty on delivery | 2026-05-06 | Ben Ward | Low | Replaced under warranty before engineer training | Closed | 2026-05-12
I04 | UAT: VAT rounding error on quote PDF template | 2026-05-20 | Tom Reilly | Medium | Template fixed by supplier and retested before go/no-go | Closed | 2026-05-22

## Assumptions
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
RAID log: assumptions
ID | Assumption | Owner | Validation
A01 | 18 named CRM users is enough for year 1 (office team plus 6 tablet users) | Helen Marsh | Validated at go-live
A02 | Key users can give one day a week to workshops, UAT and training | Dave Pearson | Held, with backfill
A03 | The existing accounting package stays in place | Lucy Bell | Held
A04 | Office broadband and engineers' 4G are adequate for a cloud CRM | Ben Ward | Held; offline mode covers gaps

## Dependencies
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
RAID log: dependencies
ID | Dependency | Owner | Needed by | Status
D01 | Accounting package API access and connector licence | Lucy Bell | Before task 3.4 | Met (via CR01)
D02 | Tablets delivered and enrolled before engineer training | Ben Ward | Before task 6.4 | Met
D03 | Email domain admin access from Quayside IT | Ben Ward | Before task 3.4 | Met
D04 | Sponsor available for go/no-go decision | Helen Marsh | M5 | Met

## Change log
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
Change control log
Any change over £500 or affecting a milestone needs sponsor approval (charter tolerances).
CR | Change | Raised | Cost | Schedule impact | Decision
CR01 | Paid accounting connector and 3 extra supplier days for invoice sync | 2026-04-20 | £900 | +3 working days on task 3.4 (not on critical path) | Approved by sponsor

## Scoring key
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
Risk scoring matrix (probability × impact)
Probability ↓ / Impact → | 1 | 2 | 3 | 4 | 5
5 | 5 | 10 | 15 | 20 | 25
4 | 4 | 8 | 12 | 16 | 20
3 | 3 | 6 | 9 | 12 | 15
2 | 2 | 4 | 6 | 8 | 10
1 | 1 | 2 | 3 | 4 | 5