## RACI
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
RACI matrix
R = Responsible, A = Accountable (exactly one per row), A/R = accountable and doing the work, C = Consulted, I = Informed. The check column is a formula.
Activity / deliverable | Sponsor (HM) | Project Manager (PM) | Ops Manager (DP) | Office Manager (PS) | Sales Lead (TR) | Field Supervisor (GH) | Finance (LB) | Supplier (SC) | IT Support (BW) | One A?
Business case and charter | A | R | C | C | C | I | C | I | I | 0
Stakeholder analysis | C | A/R | C | C | I | I | I |  |  | 0
Process mapping and requirements | I | A | R | R | R | C | C | C |  | 0
Supplier selection and contract | A | R | C | C | C | I | C |  | C | 0
Solution design and configuration | I | A | C | C | C | C | C | R | C | 0
Accounting and email integration | I | A |  | I |  |  | C | R | R | 0
Data cleansing and migration | I | A | C | R | C |  | C | R |  | 0
User acceptance testing | I | R | A | R | R | R | R | C |  | 0
Training and change | I | A | C | R | C | R | I | C |  | 0
Go/no-go decision | A | R | C | C | I | C | C | C | I | 0
Hypercare and handover to BAU | I | A | R | R | I | C | I | C | C | 0
Budget tracking and change control | A | R | I |  |  |  | C | C |  | 0
Closure and lessons learned | A | R | C | C | C | C | C | C | I | 0
Count of R per role (formula) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Names: HM Helen Marsh · PM Chidera Ikenna-Obi (simulated PM role) · DP Dave Pearson · PS Priya Shah · TR Tom Reilly · GH Gary Hodgson · LB Lucy Bell · SC Sam Carter · BW Ben Ward. All except the PM are fictional.

## Communications plan
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
Communications plan
Linked to the stakeholder register: high-power, high-interest stakeholders get the most frequent, two-way contact.
Communication | Audience | Purpose | Channel | Frequency | Owner | Artefact used
Project kick-off | All staff | Explain why, what changes and when | Team meeting (in person) | Once, week 2 | Helen Marsh | Charter summary slide
Sponsor 1:1 | Sponsor | Decisions, risks, tolerance check | Meeting (30 min) | Fortnightly | Chidera Ikenna-Obi | Status dashboard
Weekly project meeting | Core team (DP, PS, TR, GH, LB) | Progress, actions, RAID review | Meeting (45 min) | Weekly | Chidera Ikenna-Obi | RAID log, schedule
Supplier check-in | Supplier, PM | Configuration progress, change requests | Video call | Weekly | Chidera Ikenna-Obi | Action log, CR log
Highlight report | Sponsor, Ops Manager | RAG status, milestones, budget | Email (one page) | Fortnightly | Chidera Ikenna-Obi | Status dashboard
Toolbox talk | Field engineers | What the app does for them; feedback | Depot briefing (10 min) | Monthly, then weekly in May | Gary Hodgson | Demo on tablet
Champions huddle | Office champions | Questions, workarounds, readiness | Stand-up (15 min) | Weekly from week 8 | Priya Shah | Readiness checklist
Go-live notice | All staff | Cut-over timing, support rota, who to ask | Email and noticeboard | Week before go-live | Chidera Ikenna-Obi | Go-live checklist
Customer notice | Customers | New reminder and quote emails | Website and email footer | At go-live | Priya Shah | Approved wording
Closure briefing | Sponsor, all staff | Results, lessons, what happens next | Team meeting | Once, at closure | Helen Marsh | Closure report