## Dashboard
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
Project Compass: project status dashboard
Cobbleway Home Services Ltd (fictional) · CRM implementation · Highlight report 5 · Project manager: Chidera Ikenna-Obi (simulated role)
Status date (input) | 2026-05-08 | Week 10 of 15 |  |  |  | Overall RAG | 0
RAG summary | [5 empty] | Key figures
Dimension | RAG | How it is calculated |  |  |  | Total budget (incl. contingency) |  | Actual spend to date |  | Forecast at completion
Schedule | 0 | Worst forecast milestone slip: 0 = G, 1–5 wd = A, >5 wd (tolerance) = R |  |  |  | 0 |  | 0 |  | 0
Cost | 0 | EAC ≤ base = G; within contingency = A; above total budget = R
Scope | 0 | Manual: all Must requirements in plan; CR01 approved |  |  |  | Contingency remaining |  | Milestones achieved |  | Open risks
Risks | 0 | Open risks scoring 15+: 0 = G, 1 = A, 2+ = R |  |  |  | 0 |  | 0% |  | 0
Issues | 0 | Any open High issue = A
Milestone tracker | [5 empty] | Risk heatmap (open risks at status date)
Milestone | Baseline | Forecast / actual | Variance (wd) | Status | RAG | Probability ↓ Impact → | 1 | 2 | 3 | 4 | 5
0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | Numbers = count of open risks in each cell. Source: Risks sheet (from the RAID log).
0 | 0 | 0 | 0 | 0 | 0
Budget vs actual (GBP)
Category | Budget | Actual to date | Forecast (EAC) | Variance | % spent
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
PM commentary (status date)
Amber overall. Data cleansing (task 4.1) is forecast to finish 10 working days late because ~18% of legacy records are duplicates (issue I01). Go-live is forecast for 27 May against a 20 May baseline: a 4 working-day slip, inside the 1-week tolerance. CR01 (accounting connector, £900) approved. EAC is £1,780 over base budget and within contingency. Decision needed: none. Next: complete cleansing, trial migration, UAT from 19 May.
Issues at status date
Issue | ID | Severity | Raised | At status date
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0
Next fortnight
• Finish data cleansing (4.1) and run trial migration with reconciliation (4.2)
• Complete configuration (M4, 12 May); tablets enrolled and tested offline
• Office and field training 14–15 May; UAT 19–22 May; go/no-go 22 May

## Milestones
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
Milestone data
Forecast = latest forecast at the status date (actual if achieved).
WBS | Milestone | Baseline | Forecast / actual | Variance (wd)
1.4 | M1 Charter and business case approved | 2026-03-11 | 2026-03-11 | 0
2.3 | M2 Requirements signed off | 2026-03-24 | 2026-03-24 | 0
2.5 | M3 Supplier selected and contract signed | 2026-04-07 | 2026-04-07 | 0
3.6 | M4 Configuration complete | 2026-05-12 | 2026-05-12 | 0
5.3 | M5 Go/no-go decision | 2026-05-18 | 2026-05-22 | 0
7.2 | M6 Go-live | 2026-05-20 | 2026-05-27 | 0
8.3 | M7 Project closed | 2026-06-10 | 2026-06-16 | 0
Formulas:
Variance (wd) = IF([Forecast / actual]>=[Baseline],NETWORKDAYS([Baseline],[Forecast / actual],Holidays)-1,-(NETWORKDAYS([Forecast / actual],[Baseline],Holidays)-1))

## Budget
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
Budget vs actual (GBP)
Actual to date at status date 08 May 2026. EAC = estimate at completion.
Category | Budget | Actual to date | Forecast (EAC) | Variance (EAC − budget) | % spent
CRM licences (18 users, year 1) | 6800 | 6800 | 6800 | 0 | 0%
Supplier configuration and integration | 9500 | 7600 | 10400 | 0 | 0%
Data migration and cleansing | 4200 | 4200 | 4900 | 0 | 0%
Training and materials | 3000 | 600 | 3000 | 0 | 0%
Internal staff time (backfill) | 6000 | 3900 | 6300 | 0 | 0%
Hardware (6 rugged tablets and cases) | 3500 | 3380 | 3380 | 0 | 0%
Base budget total | 0 | 0 | 0 | 0 | 0%
Contingency (10.6% of base) | 3500
Total approved budget (incl. contingency) | 0
Contingency remaining at EAC | 0

## Spend profile
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
Cumulative spend profile (GBP)
Actual for May is to the status date only.
Month | Planned (cumulative) | Actual (cumulative)
Mar 2026 | 2100 | 2050
Apr 2026 | 17400 | 18350
May 2026 | 28900 | 26480
Jun 2026 | 33000

## Risks
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
Risk data (copy of RAID log risks)
Heatmap counts risks open at the status date: raised on or before it and not closed by then.
ID | Risk | Raised | Prob. | Impact | Score | Closed
R01 | Poor legacy data quality delays migration | 2026-03-09 | 4 | 4 | 0 | 2026-05-18
R02 | Field engineers do not adopt the mobile app | 2026-03-09 | 3 | 4 | 0
R03 | Accounting integration more complex than quoted | 2026-03-23 | 3 | 4 | 0 | 2026-04-27
R04 | Key staff unavailable for UAT and training | 2026-03-16 | 3 | 3 | 0 | 2026-05-15
R05 | Supplier resourcing slips configuration | 2026-04-02 | 2 | 4 | 0 | 2026-05-12
R06 | Customer data migrated without proper retention review | 2026-03-16 | 2 | 5 | 0 | 2026-05-27
R07 | Change requests push cost over tolerance | 2026-04-13 | 3 | 3 | 0 | 2026-06-16
R08 | Low mobile signal stops job updates | 2026-03-23 | 3 | 2 | 0 | 2026-05-15
R09 | Go-live disrupts customer service | 2026-04-20 | 2 | 4 | 0 | 2026-06-10

## Issues
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
Issue data (copy of RAID log issues)
ID | Issue | Raised | Severity | Closed
I01 | Around 18% of legacy customer records are duplicates | 2026-04-21 | High | 2026-05-13
I02 | Accounting package needs a paid connector for invoice sync | 2026-04-16 | Medium | 2026-04-27
I03 | Two tablets faulty on delivery | 2026-05-06 | Low | 2026-05-12
I04 | UAT: VAT rounding error on quote PDF template | 2026-05-20 | Medium | 2026-05-22

## Holidays
⚠ SIMULATED PROJECT: FICTIONAL COMPANY, CREATED FOR PORTFOLIO AND LEARNING PURPOSES · Cobbleway Home Services Ltd is not a real business
UK bank holidays
Date | Holiday
2026-04-03 | Good Friday
2026-04-06 | Easter Monday
2026-05-04 | Early May bank holiday
2026-05-25 | Spring bank holiday